## Sheet1
| Estimated |  | Actual
Task | Dev(Hrs) | UI(Hrs) | Dev(Hrs ) | UI(Hrs )
Project creation with required dependancies | 1 |  | 0.5
Entity creation | 1 |  | 0.45
Service classes creation | 1 |  | 1.2
All movies component | 1 | 1 | 1 | 1
Category View component | 1 | 1 | 0.8 | 1
Movie preview component | 1 | 2 | 1 | 1
Movie full view component | 1 | 2 | 0.9 | 1.4
Navigation features | 3 |  | 2
Video player integration | 1.5 | 1.5 | 3.5 | 0.1
Integration all components | 2 |  | 2
Responsiveness improvement | 1 | 2 | 1 | 1.75
| 14.5 | 9.5 | 14.35 | 6.25
|  | 24Hrs |  | 20.6Hrs
|  | ~3md |  | ~3md
Task | Dev(Hrs) | UI(Hrs)
Project creation with required dependancies | 0.5
Entity creation | 0.45
Service classes creation | 1.2
All movies component | 1 | 1
Category View component | 0.8 | 1
Movie preview component | 1 | 1
Movie full view component | 0.9 | 1.4
Navigation features | 2
Video player integration | 3.5 | 0.1
Integration all components | 2
Responsiveness improvement | 1 | 1.75
| 14.35 | 6.25
20.6Hrs
3md